## Work_Log
Date | Hours | Actions
2025-01-26 | 2 | - Searched for datasets that could be used for the project. Websites such as Kaggle and Google Dataset Search were checked. The focus was on finding data with sales information and customer reviews
- ChatGPT’s prompts:
“what types of corpus of customer’s reviews could be?”
“customer’s review corpus in csv is considered as structured or unstructured data?”
2025-01-27 | 1.5 | - Continued searching for datasets on Kaggle, the UCI Machine Learning Repository, and Harvard Dataverse. Different datasets were reviewed to see if they met the project requirements
- ChatGPT’s prompts:
“review this dataset to see whether is it meet requirements of my project?”
“suggest sources of dataset as the project requirements”
2025-01-29 | 3 | - Looked for more datasets on Data.gov and Kaggle
- Researched data scraping techniques from web
- ChatGPT’s prompts:
“how to scrap data of sales and client’s review from a web”
“any legal issues of the scraping?”
2026-01-31 | 4 | - Selected a dataset from Kaggle due to time limits
- Set up environments (VSC, SQL Server Management System, ODBC)
- Created IBP database in SQL Server
- Created schemas for raw dataset
- Researched inserting the raw data into the database by Python
- ChatGPT’s prompts:
“which dependencies must be installed for my project?”
“how to connect backend and SQL server by python?”
“any syntax issue of this table creation?”
“how to inject data from csv into SQL server by python?”
“explain in step by step these functions”
2026-02-01 | 1 | - Loaded the raw sales and review data into the database using Python. Checked the results to make sure the data was loaded correctly.
- ChatGPT’s prompts:
“any wrong syntax or unlogic of this function? and correct it”
“explain in details these statements”
2026-02-02 | 4 | - Studied data cleaning methods using Python.
- Created clean tables using dimension and fact tables in SQL Server.
- Transformed raw data into clean data
- ChatGPT’s prompts:
“why should have dim and fact tables?”
“dim & fact are for normalization purpose, is it right?”
2026-02-03 | 3 | - Studied how to prepare data for Power BI.
- Created analysis tables and a summary view in SQL Server.
- ChatGPT’s prompts:
“why don’t use data directly from the clean tables, instead of creating new analysis tables?”
“why used view instead of creating another analysis table? ”
2026-02-04 | 4 | - Drafted the project progress report
- ChatGPT’s prompts:
“wording these paragraphs”
2026-02-06 | 2 | - Updated the progress report
- Research about FastAPI to connect html front-end with backend by python
- ChatGPT’s prompts:
“how can use fastapi to connect a html frontend and backend in python”
“explain these api in details, line by line”
2026-02-08 | 1.5 | - Researched front-end's frameworks for uploading the dataset
- ChatGPT’s prompts:
“which framework works best with html + fastApi?”
“compare bootstrap and tailwind”
“why should use jinja template?, what if not using it”
2026-02-09 | 2 | - Started developing the FastAPI backend structure.
- ChatGPT’s prompts:
“debug these code”
“explain in details these statements”
2026-02-10 | 3 | - Kept developing the FastAPI backend structure.
- Tested basic API endpoint to confirm backend server runs correctly.
- ChatGPT’s prompts:
“debug these code”
“explain in details these statements”
2026-02-11 | 3 | - Developed file upload endpoint in FastAPI
- Tested uploading CSV files from local machine.
- ChatGPT’s prompts:
“debug these code”
“explain in details these statements”
2026-02-13 | 2 | - Developed basic HTML form for dataset upload.
- Integrated frontend form with FastAPI backend endpoint.
- ChatGPT’s prompts:
"how to connect html form with fastapi backend?”
“debug these code”
“explain in details these statements”
2026-02-15 | 2.5 | - Improved frontend layout using Bootstrap.
- Organized upload section and status display messages.
- Tested full upload-to-database pipeline again.
- ChatGPT’s prompts:
“how to display successful response in html”
“debug these code”
“explain in details these statements”
2026-02-17 | 3 | - Tested layering process in SQL Server after frontend upload.
- Verified raw -> clean -> analytics transformation works correctly.
- Fixed issues in foreign key relationships.
- ChatGPT’s prompts:
“why foreign key constraint failed?”
“debug these code”
“explain in details these statements”
2026-02-18 | 2 | - Improved SQL aggregation queries in analytics layer.
- Tested daily and monthly summary tables.
- ChatGPT’s prompts:
“debug these code”
“explain in details these statements”
2026-02-21 | 3 | - Draft the midterm report
- ChatGPT’s prompts:
“wording these paragraphs”
2026-02-22 | 3 | - Draft the midterm report
- Outlined structure of the demo video:
- ChatGPT’s prompts:
“wording these paragraphs”
2026-02-23 | 4 | - Made the video, finalized the midterm report
2026-02-24 | 2 | - Build front-end for dashboard
- Reseached on html navigation in FastAPI
- ChatGPT’s prompts:
“why cannot navigate between html pages”
“how to do html navigation in fastApi?”

## Timeline
INITIAL PLAN
MILESTONES | January | February |  |  |  | March |  |  |  | April |  |  |  | April
| W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1
1. Database & design
2. ELT pipeline
3. Backend & UI
4. Business Analytics & Dashboard
5. Forecast & Recommendation
6. Reporting & UI Interaction
7. Final review
THE ADJUSTED PLAN
MILESTONES | January | February |  |  |  | March |  |  |  | April |  |  |  | April
| W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1
1. Database & design
2. ELT pipeline
3. Backend & UI
4. Business Analytics & Dashboard
5. Forecast & Recommendation
6. Reporting & UI Interaction
7. Final review